## Sheet1
Task | Start Date | Days To Complete | Group Member
Client GUI | 2018-11-08 | 12 | Skyler
Client Communication | 2018-11-08 | 10 | Skyler
Server GUI | 2018-11-08 | 2 | Alex
Server Communication | 2018-11-08 | 10 | Alex
Login | 2018-11-11 | 5 | Alex
Game Mechanics | 2018-11-08 | 8 | Garrett
Create Account | 2018-11-11 | 5 | Anish
Custom Exception | 2018-11-08 | 10 | Skyler
Database SQL | 2018-11-08 | 3 | Garrett
Database Communication | 2018-11-11 | 5 | Garrett
Unit Testing (GM) | 2018-11-16 | 4 | Anish
Unit Testing (L/CA) | 2018-11-16 | 4 | Skyler
Integration Testing | 2018-11-18 | 2 | Garrett
Final Testing | 2018-11-20 | 2 | Skyler